## RMS
Type | Screen/Function | Description | Function group | In Charge | SRS | SDS | Status | Notes
Function | Add Product | As a Store Manager, I want to create new products so that stores can update and expand product offerings. | product | Nam Khánh |  |  | To Do
Function | add category |  | product | Nam Khánh |  |  | Done
Function | active, inactive category |  | product | Nam Khánh |  |  | Done
Function | Create Voucher |  | voucher | Trung Kiên |  |  | Done
Function | Create voucher |  | voucher | Trung Kiên |  |  | Done
Function | Set time for voucher |  | voucher | Trung Kiên |  |  | Done
Function | Inactive voucher |  | voucher | Trung Kiên |  |  | Done
Function | Active voucher |  | voucher | Trung Kiên |  |  | Done
Function | Delete voucher |  | voucher | Trung Kiên |  |  | Done
Function | User Login | As a user, I want to log in to the system using username/password so that I can access functions based on my role. | staff account | Vũ Hùng |  |  | Done
Function | User Logout | As a user, I want to log out of the system so that my account is protected when I stop using the system. | staff account | Vũ Hùng |  |  | Done
Function | CRUD employee |  | staff account | Vũ Hùng |  |  | Done
Function | Reset User Password |  | staff account | Vũ Hùng |  |  | Done
Function | View Access Denied Message | As a user, I want to see an access denied message when I do not have permission so that I understand why I cannot use that function. | staff account | Vũ Hùng |  |  | Done
Function | Create Branch |  | Branch | Vũ Hùng |  |  | Done
Function | Update Branch |  | Branch | Vũ Hùng |  |  | Done
Function | View List Branch |  | Branch | Vũ Hùng |  |  | Done
Function | Find Branch |  | Branch | Vũ Hùng
Function | Delete Branch |  | Branch | Vũ Hùng |  |  | Done
Function | Create Branch |  | Branch | Vũ Hùng |  |  | Done
Function | add brand |  | product | Nam Khánh |  |  | Done
Function | update brand |  | product | Nam Khánh |  |  | Done
Function | add unit |  | product | Nam Khánh |  |  | Done
Function | update unit |  | product | Nam Khánh |  |  | Done
Function | add productUnit |  | product | Nam Khánh |  |  | Done
Function | update productUnit |  | product | Nam Khánh |  |  | Done
Function | Customer List |  | customer | Kim Anh |  |  | Done
Function | Create New Customer |  | customer | Kim Anh |  |  | Done
Function | Update Customer |  | customer | Kim Anh |  |  | Done
Function | View Details |  | customer | Kim Anh |  |  | Done
Function | Find Customer |  | customer | Kim Anh |  |  | Done
Function | View Customer |  | customer | Kim Anh |  |  | Done
Function | Page Access Control |  | Authorize | Vũ Hùng |  |  | To Do
Function | Create Import transaction |  | Import | Vũ Hùng |  |  | To Do
Function | Set max, min for product in inventory |  | Inventory | Vũ Hùng |  |  | To Do
Function | Create Inventory | As a shop owner, I want to inventory autocreation after create branch so that I can manager inventory | Inventory | Vũ Hùng |  |  | To Do
Function | Edit Inventory |  | Inventory | Vũ Hùng |  |  | To Do
Function | Auto create inventory when create branch |  | Inventory | Vũ Hùng |  |  | To Do
Function | View Inventory Details |  | Inventory | Vũ Hùng
Function | Filter Low Stock |  | Inventory | Vũ Hùng
Function | View Inventory Summary by Branch |  | Inventory | Vũ Hùng
Function | Header/ naviagator |  | Frontend | Trung Kiên |  |  | Done
Function | Page design |  | Frontend | Trung Kiên |  |  | Done
Function | Check Customer Purchase Branch | As a Cashier, I want to identify which branch the customer purchased from so that purchase history can be verified accurately. | Report | Trung Kiên |  |  | To Do
Function | Manage Cashbook | As a user (Accountant, Owner), I want to track the balance of cash and bank deposits for each branch so that I can control the chain's finances. | Report | Trung Kiên |  |  | To Do
Function | View Business Report | As a user (Admin, Store Manager), I want to see the profit report (Revenue - Expenses) for a specific period to evaluate business performance. | Report | Trung Kiên |  |  | To Do
Function | Show Cash Flow Chart | As an Admin/Owner, I want to view cash flow charts to identify the financial trends of each specific store in the chain. | Report | Trung Kiên |  |  | To Do
Function | Add voucher rank |  | voucher | Trung Kiên
Function | Search Product | As a Cashier, I want to search for products quickly so that customer service can be improved during sales transactions. | product | Nam Khánh |  |  | To Do
Function | View Product Details | As a Cashier, I want to view product details so that I can provide accurate product information to customers. | product | Nam Khánh |  |  | To Do
Function | Pagging in product list |  | product | Nam Khánh
Function | Product Stock Checking | As a Warehouse Staff member, I want to check stock quantities so that inventory shortages or overstock situations can be identified early. | product | Nam Khánh |  |  | To Do
Function | Allow create unit in product page |  | product | Nam Khánh
Function | update supplier |  | supplier | Nam Khánh |  |  | To Do
Function | Create supplier | As a shop owner, I want to create supplier so that I can Import product, restock | supplier | Nam Khánh |  |  | To Do
Function | Edit supplier |  | supplier | Nam Khánh |  |  | To Do
Function | Delete supplier |  | supplier | Nam Khánh |  |  | To Do
Function | View supplier list |  | supplier | Nam Khánh |  |  | To Do
Function | Export Customer File | As a Store Manager, I want to export customer data to file so that I can analyze customer information or create report | customer | Kim Anh |  |  | To Do
Function | View Customer Loyalty Information | As a Cashier, I want to view customer reward points and promotions so that eligible customers can receive appropriate benefits. | customer | Kim Anh |  |  | To Do
Function | Add Customer Point | As a Cashier, I want to add bonus point per purcahse so that customer can have bonus point and promotion | order | Kim Anh |  |  | To Do
Function | Add Customer Voucher | As a Chain Store Manager and Store Manager, I want to add voucher for specific customer so that they can have benefit | order | Kim Anh |  |  | To Do
Function | Apply Discount | As a Store Manager, I want to create and apply discounts or promotions so that stores can attract more customers and increase sales. | order | Kim Anh |  |  | To Do
Function | Manage Sales Transactions | As a Shop owner, I want to manage all sales transactions so that the entire chain store system can be controlled effectively. | order | Kim Anh |  |  | To Do
Function | Create Promotion | As a Store Manager, I want to create promotions so that stores can increase customer engagement and sales revenue. | order | Kim Anh |  |  | To Do
Function | Create bill | As a Cashier, I want to create sales invoices so that customer purchases can be processed and recorded in the system. | order | Kim Anh |  |  | To Do
Function | Update bill | As a Cashier, I want to update invoice information so that transaction mistakes can be corrected before payment confirmation. | order | Kim Anh |  |  | To Do
Function | Add Products to bill | As a Cashier, I want to add products to invoices so that customers can purchase multiple products in one transaction. | order | Kim Anh |  |  | To Do
Function | Remove Products from bill | As a Cashier, I want to remove products from invoices so that order changes can be handled quickly and accurately. | order | Kim Anh |  |  | To Do
Function | Calculate Total Amount | As a Cashier, I want the system to automatically calculate the total amount so that billing becomes faster and more accurate. | order | Kim Anh |  |  | To Do
Function | Process Payment | As a Cashier, I want to process payments so that customer transactions can be completed successfully. | order | Kim Anh |  |  | To Do
Function | Print Bill | As a Cashier, I want to print bill so that customers can receive purchase receipts after payment. | order | Kim Anh |  |  | To Do
Function | View Sales History | As a Store Manager, I want to view sales history so that branch sales performance can be monitored and reviewed. | order | Kim Anh |  |  | To Do
Function | Send email when fogot password |  | Authorize | Vũ Hùng |  |  | Done
Function | Create Import requirement |  | Import | Vũ Hùng |  |  | Done
Function | Confirm import requirement |  | Import | Vũ Hùng |  |  | Done
Function | Cancel Import requirement |  | Import | Vũ Hùng |  |  | Done
Function | Payment Method Tracking | As an accountant, I want to categorize cash flow by cash, bank transfer so that I can easily reconcile with bank statements. | Report | Trung Kiên |  |  | Done
Function | Branch-based Filter | As a user (Admin, Accountant), I want to filter transaction data by Branch (Store ID) so that I can manage finances for each location independently. | Report | Trung Kiên |  |  | Done
Function | Sales employee report |  | Report | Trung Kiên |  |  | Done
Function | Export Financial Data | As an accountant, I want to export the transaction list to Excel so that I can perform further accounting tasks or archiving. | Report | Trung Kiên |  |  | Done
Function | Allow create brand in product page |  | product | Nam Khánh |  |  | Done
Function | Allow create category in product page |  | product | Nam Khánh |  |  | Done
Function | Add Search Unit when create product |  | product | Nam Khánh |  |  | Done
Function | Add Search brand when create product |  | product | Nam Khánh |  |  | Done
Function | Add Search category when create product |  | product | Nam Khánh |  |  | Done
Function | Product filer |  | product | Nam Khánh |  |  | Done
Function | Return product |  | order | Kim Anh |  |  | Done
Function | Use point in order | As a Customer, I want to use point to minus order amount | order | Kim Anh |  |  | Done
Function | minus stock when complete order |  | order | Kim Anh |  |  | Done
Function | Not show inactive product when create order |  | order | Kim Anh |  |  | Done
Function | Inventory report |  | Report | Nam Khánh |  |  | Done
Function | Allow create and add supplier when create product |  | product | Vũ Hùng |  |  | Done
Function | Transfer between branch |  | Transaction | Vũ Hùng |  |  | Done
Function | Employee report |  | Report | Trung Kiên |  |  | Done
Function | Total report |  | Report | Trung Kiên |  |  | Done
Function | Page Access Control |  | Authorize | Xuân Huy |  |  | To Do
Function | Edit Inventory | As a shop owner, I want to inventory autocreation after create branch so that I can manager inventory | Inventory | Vũ Hùng |  |  | To Do
Function | Delet Inventory |  | Inventory | Vũ Hùng
Function | Auto create inventory when create branch |  | Inventory | Vũ Hùng
Note on D1: ====== ID#AAAB7CZm-mQ KienNT (2026-05-24 05:36:46) Phân tích yêu cầu và thiết kế cho màn hình/chức năng được mô tả trong phần nào của tài liệu SDS?
Note on E1: ====== ID#AAAB7CZm-mY KienNT (2026-05-24 05:36:46) Phân tích yêu cầu và thiết kế cho màn hình/chức năng được mô tả trong phần nào của tài liệu SDS?

## Iter1
Type | Screen/Function | Description | Function group | In Charge | SRS | SDS | Status | Notes
Report | Use case | Sale |  | Kim Anh |  |  | Doing
Report | ERD | customer |  | Kim Anh |  |  | Doing
Report | ERD | reward_point_histories |  | Kim Anh |  |  | Doing
Report | ERD | customers_ranks |  | Kim Anh |  |  | Doing
Report | ERD | employees |  | Kim Anh |  |  | Doing
Report | ERD | Voucher |  | Kim Anh |  |  | Doing
Report | Context Diagram | Draw Context Diagram |  | Kim Anh |  |  | Done
Report | DB design | customer |  | Kim Anh |  |  | To Do
Report | DB design | reward_point_histories |  | Kim Anh |  |  | To Do
Report | DB design | customers_ranks |  | Kim Anh |  |  | To Do
Report | DB design | employees |  | Kim Anh |  |  | To Do
Report | DB design | Voucher |  | Kim Anh |  |  | To Do
Report | Context Diagram | change "Cashier" to "Sale", "Chain manager" to "Shop Owner" |  | Nam Khánh |  |  | Done
Report | Use case | Shop owner |  | Nam Khánh |  |  | Done
Report | ERD | categories |  | Nam Khánh |  |  | Doing
Report | ERD | brand |  | Nam Khánh |  |  | Doing
Report | ERD | product_images |  | Nam Khánh |  |  | Doing
Report | ERD | Unit |  | Nam Khánh |  |  | Doing
Report | ERD | ProductUnit |  | Nam Khánh |  |  | Doing
Report | ERD | InventoryConfig, |  | Nam Khánh |  |  | Doing
Report | ERD | Product |  | Nam Khánh |  |  | Doing
Report | ERD | stockTransaction |  | Nam Khánh |  |  | Doing
Report | ERD | Supplier |  | Nam Khánh |  |  | Doing
Report | ERD | Inventories |  | Nam Khánh |  |  | Doing
Report | ERD | InventoryConfig |  | Nam Khánh |  |  | Doing
Report | ERD | stockHistory |  | Nam Khánh |  |  | Doing
Report | ERD | ImportOrder |  | Nam Khánh |  |  | Doing
Report | ERD | ImportOrderItem |  | Nam Khánh |  |  | Doing
Report | ERD | PaymentMethod |  | Nam Khánh |  |  | Doing
Report | Context Diagram | Draw Context Diagram |  | Nam Khánh |  |  | Done
Report | Create DB |  |  | Nam Khánh |  |  | To Do
Report | DB design | categories |  | Nam Khánh |  |  | Done
Report | DB design | brand |  | Nam Khánh |  |  | Done
Report | DB design | product_images |  | Nam Khánh |  |  | Done
Report | DB design | Unit |  | Nam Khánh |  |  | Done
Report | DB design | ProductUnit |  | Nam Khánh |  |  | Done
Report | DB design | InventoryConfig, |  | Nam Khánh |  |  | Done
Report | DB design | Product |  | Nam Khánh |  |  | Done
Report | DB design | stockTransaction |  | Nam Khánh |  |  | Done
Report | DB design | Supplier |  | Nam Khánh |  |  | Done
Report | DB design | Inventories |  | Nam Khánh |  |  | Done
Report | DB design | InventoryConfig |  | Nam Khánh |  |  | Done
Report | DB design | stockHistory |  | Nam Khánh |  |  | Done
Report | DB design | ImportOrder |  | Nam Khánh |  |  | Done
Report | DB design | ImportOrderItem |  | Nam Khánh |  |  | Done
Report | DB design | PaymentMethod |  | Nam Khánh |  |  | Done
Function | Add Product | As a Store Manager, I want to create new products so that stores can update and expand product offerings. | product | Nam Khánh |  |  | To Do
Function | add category |  | product | Nam Khánh |  |  | Done
Function | active, inactive category |  | product | Nam Khánh |  |  | Done
Report | Use case | Warehouse |  | Trung Kiên |  |  | Done
Report | UI design | dashboard store manage |  | Trung Kiên |  |  | Done
Report | UI design | dashboard warehouse staff |  | Trung Kiên |  |  | Done
Report | UI design | dashboard sales staf |  | Trung Kiên |  |  | Done
Report | UI design | dashboard login |  | Trung Kiên |  |  | Done
Function | Create Voucher |  | voucher | Trung Kiên |  |  | Done
Function | Create voucher |  | voucher | Trung Kiên |  |  | Done
Function | Set time for voucher |  | voucher | Trung Kiên |  |  | Done
Function | Inactive voucher |  | voucher | Trung Kiên |  |  | Done
Function | Active voucher |  | voucher | Trung Kiên |  |  | Done
Function | Delete voucher |  | voucher | Trung Kiên |  |  | Done
Report | Context Diagram | change "payment system" to "Vnpay" |  | Vũ Hùng |  |  | Done
Report | Context Diagram | Draw Context Diagram |  | Vũ Hùng |  |  | Done
Report | Use case | Store manager |  | Vũ Hùng |  |  | Done
Report | UI design | dashboard shop owner |  | Vũ Hùng |  |  | Done
Report | UI design | Sales management page |  | Vũ Hùng |  |  | Done
Report | UI design | Customers |  | Vũ Hùng |  |  | Done
Report | UI design | Products |  | Vũ Hùng |  |  | Done
Report | UI design | Employees |  | Vũ Hùng |  |  | Done
Report | UI design | Branches |  | Vũ Hùng |  |  | Done
Function | User Login | As a user, I want to log in to the system using username/password so that I can access functions based on my role. | staff account | Vũ Hùng |  |  | Done
Function | User Logout | As a user, I want to log out of the system so that my account is protected when I stop using the system. | staff account | Vũ Hùng |  |  | Done
Function | CRUD employee |  | staff account | Vũ Hùng |  |  | Done
Function | Reset User Password |  | staff account | Vũ Hùng |  |  | Done
Function | View Access Denied Message | As a user, I want to see an access denied message when I do not have permission so that I understand why I cannot use that function. | staff account | Vũ Hùng |  |  | Done
Function | Create Branch |  | Branch | Vũ Hùng |  |  | Done
Function | Update Branch |  | Branch | Vũ Hùng |  |  | Done
Function | View List Branch |  | Branch | Vũ Hùng |  |  | Done
Function | Find Branch |  | Branch | Vũ Hùng
Function | Delete Branch |  | Branch | Vũ Hùng |  |  | Done
Function | Create Branch |  | Branch | Vũ Hùng |  |  | Done
Report | Context Diagram | Draw Context Diagram |  | Xuân Huy |  |  | Done
Report | Use case | Accountant |  | Xuân Huy |  |  | Done
Report | ERD | businesses |  | Xuân Huy |  |  | Doing
Report | ERD | branches |  | Xuân Huy |  |  | Doing
Report | ERD | roles |  | Xuân Huy |  |  | Doing
Report | ERD | accounts |  | Xuân Huy |  |  | Doing
Report | DB design | businesses |  | Xuân Huy |  |  | Done
Report | DB design | branches |  | Xuân Huy |  |  | Done
Report | DB design | roles |  | Xuân Huy |  |  | Done
Report | DB design | accounts |  | Xuân Huy |  |  | Done
Function | add brand |  | product | Nam Khánh |  |  | Done
Function | update brand |  | product | Nam Khánh |  |  | Done
Function | add unit |  | product | Nam Khánh |  |  | Done
Function | update unit |  | product | Nam Khánh |  |  | Done
Function | add productUnit |  | product | Nam Khánh |  |  | Done
Function | update productUnit |  | product | Nam Khánh |  |  | Done
Function | Customer List |  | customer | Kim Anh |  |  | Done
Function | Create New Customer |  | customer | Kim Anh |  |  | Done
Function | Update Customer |  | customer | Kim Anh |  |  | Done
Function | View Details |  | customer | Kim Anh |  |  | Done
Function | Find Customer |  | customer | Kim Anh |  |  | Done
Function | View Customer |  | customer | Kim Anh |  |  | Done
Note on D1: ====== ID#AAAB7CZm-mc KienNT (2026-05-24 05:36:46) Phân tích yêu cầu và thiết kế cho màn hình/chức năng được mô tả trong phần nào của tài liệu SDS?
Note on E1: ====== ID#AAAB7CZm-mU KienNT (2026-05-24 05:36:46) Phân tích yêu cầu và thiết kế cho màn hình/chức năng được mô tả trong phần nào của tài liệu SDS?

## Iter2
Type | Screen/Function | Description | Function group | In Charge | SRS | SDS | Status | Notes
Function | Page Access Control |  | Authorize | Vũ Hùng |  |  | Done
Function | Create Import transaction |  | Import | Vũ Hùng |  |  | Done
Function | Set max, min for product in inventory |  | Inventory | Vũ Hùng |  |  | Done
Function | Create Inventory | As a shop owner, I want to inventory autocreation after create branch so that I can manager inventory | Inventory | Vũ Hùng |  |  | Done
Function | Edit Inventory |  | Inventory | Vũ Hùng |  |  | Done
Function | Auto create inventory when create branch |  | Inventory | Vũ Hùng |  |  | Done
Function | View Inventory Details |  | Inventory | Vũ Hùng |  |  | Done
Function | Filter Low Stock |  | Inventory | Vũ Hùng |  |  | Done
Function | View Inventory Summary by Branch |  | Inventory | Vũ Hùng |  |  | Done
Function | Header/ naviagator |  | Frontend | Trung Kiên |  |  | Done
Function | Page design |  | Frontend | Trung Kiên |  |  | Done
Function | Check Customer Purchase Branch | As a Cashier, I want to identify which branch the customer purchased from so that purchase history can be verified accurately. | Report | Trung Kiên |  |  | Done
Function | Manage Cashbook | As a user (Accountant, Owner), I want to track the balance of cash and bank deposits for each branch so that I can control the chain's finances. | Report | Trung Kiên |  |  | Done
Function | View Business Report | As a user (Admin, Store Manager), I want to see the profit report (Revenue - Expenses) for a specific period to evaluate business performance. | Report | Trung Kiên |  |  | Done
Function | Show Cash Flow Chart | As an Admin/Owner, I want to view cash flow charts to identify the financial trends of each specific store in the chain. | Report | Trung Kiên |  |  | Done
Function | Add voucher rank |  | voucher | Trung Kiên |  |  | Done
Function | Search Product | As a Cashier, I want to search for products quickly so that customer service can be improved during sales transactions. | product | Nam Khánh |  |  | Done
Function | View Product Details | As a Cashier, I want to view product details so that I can provide accurate product information to customers. | product | Nam Khánh |  |  | Done
Function | Pagging in product list |  | product | Nam Khánh |  |  | Done
Function | Product Stock Checking | As a Warehouse Staff member, I want to check stock quantities so that inventory shortages or overstock situations can be identified early. | product | Nam Khánh |  |  | Done
Function | Allow create unit in product page |  | product | Nam Khánh |  |  | Done
Function | update supplier |  | supplier | Nam Khánh |  |  | Done
Function | Create supplier | As a shop owner, I want to create supplier so that I can Import product, restock | supplier | Nam Khánh |  |  | Done
Function | Edit supplier |  | supplier | Nam Khánh |  |  | Done
Function | Delete supplier |  | supplier | Nam Khánh |  |  | Done
Function | View supplier list |  | supplier | Nam Khánh |  |  | Done
Function | Export Customer File | As a Store Manager, I want to export customer data to file so that I can analyze customer information or create report | customer | Kim Anh |  |  | Done
Function | View Customer Loyalty Information | As a Cashier, I want to view customer reward points and promotions so that eligible customers can receive appropriate benefits. | customer | Kim Anh |  |  | Done
Function | Add Customer Point | As a Cashier, I want to add bonus point per purcahse so that customer can have bonus point and promotion | order | Kim Anh |  |  | Done
Function | Add Customer Voucher | As a Chain Store Manager and Store Manager, I want to add voucher for specific customer so that they can have benefit | order | Kim Anh |  |  | Done
Function | Apply Discount | As a Store Manager, I want to create and apply discounts or promotions so that stores can attract more customers and increase sales. | order | Kim Anh |  |  | Done
Function | Manage Sales Transactions | As a Shop owner, I want to manage all sales transactions so that the entire chain store system can be controlled effectively. | order | Kim Anh |  |  | Done
Function | Create Promotion | As a Store Manager, I want to create promotions so that stores can increase customer engagement and sales revenue. | order | Kim Anh |  |  | Done
Function | Create bill | As a Cashier, I want to create sales invoices so that customer purchases can be processed and recorded in the system. | order | Kim Anh |  |  | Done
Function | Update bill | As a Cashier, I want to update invoice information so that transaction mistakes can be corrected before payment confirmation. | order | Kim Anh |  |  | Done
Function | Add Products to bill | As a Cashier, I want to add products to invoices so that customers can purchase multiple products in one transaction. | order | Kim Anh |  |  | Done
Function | Remove Products from bill | As a Cashier, I want to remove products from invoices so that order changes can be handled quickly and accurately. | order | Kim Anh |  |  | Done
Function | Calculate Total Amount | As a Cashier, I want the system to automatically calculate the total amount so that billing becomes faster and more accurate. | order | Kim Anh |  |  | Done
Function | Process Payment | As a Cashier, I want to process payments so that customer transactions can be completed successfully. | order | Kim Anh |  |  | Done
Function | Print Bill | As a Cashier, I want to print bill so that customers can receive purchase receipts after payment. | order | Kim Anh |  |  | Done
Function | View Sales History | As a Store Manager, I want to view sales history so that branch sales performance can be monitored and reviewed. | order | Kim Anh |  |  | Done

## Iter3
Type | Screen/Function | Description | Function group | In Charge | SRS | SDS | Status | Note
Function | Send email when fogot password |  | Authorize | Vũ Hùng |  |  | Done
Function | Create Import requirement |  | Import | Vũ Hùng |  |  | Done
Function | Confirm import requirement |  | Import | Vũ Hùng |  |  | Done
Function | Cancel Import requirement |  | Import | Vũ Hùng |  |  | Done
Function | Payment Method Tracking | As an accountant, I want to categorize cash flow by cash, bank transfer so that I can easily reconcile with bank statements. | Report | Trung Kiên |  |  | Done
Function | Branch-based Filter | As a user (Admin, Accountant), I want to filter transaction data by Branch (Store ID) so that I can manage finances for each location independently. | Report | Trung Kiên |  |  | Done
Function | Sales employee report |  | Report | Trung Kiên |  |  | Done
Function | Export Financial Data | As an accountant, I want to export the transaction list to Excel so that I can perform further accounting tasks or archiving. | Report | Trung Kiên |  |  | Done
Function | Allow create brand in product page |  | product | Nam Khánh |  |  | Done
Function | Allow create category in product page |  | product | Nam Khánh |  |  | Done
Function | Add Search Unit when create product |  | product | Nam Khánh |  |  | Done
Function | Add Search brand when create product |  | product | Nam Khánh |  |  | Done
Function | Add Search category when create product |  | product | Nam Khánh |  |  | Done
Function | Product filer |  | product | Nam Khánh |  |  | Done
Function | Return product |  | order | Kim Anh |  |  | Done
Function | Use point in order | As a Customer, I want to use point to minus order amount | order | Kim Anh |  |  | Done
Function | minus stock when complete order |  | order | Kim Anh |  |  | Done
Function | Not show inactive product when create order |  | order | Kim Anh |  |  | Done
Function | Inventory report |  | Report | Nam Khánh |  |  | Done
Function | Allow create and add supplier when create product |  | product | Vũ Hùng |  |  | Done
Function | Transfer between branch |  | Transaction | Vũ Hùng |  |  | Done
Function | Employee report |  | Report | Trung Kiên |  |  | Done
Function | Total report |  | Report | Trung Kiên |  |  | Done